## Sheet1
Wumpus Game
| Project Name: | Wumpus Game
| Finish Date: | June 8th, 2012
2012-05-20
No | Task | Personnel | Due | Status | Notes
1 | Link buttons to game play and high score | Sarang | Two years ago | Done. | LOL in my sleep.
2 | Develop room-room movement | Sarang | 2012-05-22 | Done | Booyeah.
3 | use bats to random transport | Svetlana |  | Done
4 | use pits to end lives | Svetlana |  |  | Ask Trivia before dying.
5 | Establish a three-life game exit | Sarang |  |  | player gets three tries before the game ends on them?
6 | minimap to reveal vicinity | Svetlana |  | Almost Done
7 | show coins and arrow and time: Finishing the HUD | Sarang |  |  | quantity goes on HUD
8 | warning | Svetlana |  | In Progress | wumpus, bats, pits are nearby- where print, what parameter given? Commented out.
9 | import trivia to gameplay (implementation) | Cameron |  | In Progress
10 | pit and wind gfx | Nicholas
11 | import pit gfx | Nicholas |  |  | I think the pit would occupy the whole room…maybe make it seem like he is sliding uncontrollably towards the room center when he steps in?
12 | import wind gfx | Kevin
13 | write storyline | Svetlana |  | In progress
14 | Different Graphic: Chambers vs Rooms (colors) | Nicholas
15 | Encountering Wumpus | Svetlana |  |  | ?
17 | Correct doors - remove those that are not actually there. =P | Cameron
18 | Pause, Exit.
19 | Timing
20 | High Scores Implementation | Harrison
21 | Arrows: Shooting, Gfx, Purchasing
22 | Startup Menu implementation | Sarang
23 | Cheat Codes for Demoing |  |  |  | Rewards: Coins, arrows, time, Codes: byteme, butterchurn,
24 | Get a Butter-Churning Cheat Code. XD | Sarang |  |  | Bonus points, here we come!
25 | Secrets | Cameron |  |  | ;)
26 | Options Menu Gfx | Cameron |  | Done | Resized and implemented
27
28 | Better impact sound effect
29 | Background music
30
31
32
33
34
35